## Modules & Detail
Learning Management System
| Main Modules | Sub Modules | Details | Phase
1 | SignIn/Signup |  | The Login and signup Section for the Trainee and Instructor | 1
SignUp as a Tutor
SignUp as a Trainee
Admin Dashboard
All Tutors Info
All Trainee Info
Tutor Reports
Trainee Reports
Graphs
2 | Tutor Dashboard |  | Tutor/Instructor Dashbord is a seprate dashboard that will only be show to Instructor and will contain things like Course Ceation , Anouncemnts, Add Assignments and Quizes etc . | 2
3 | Trainee Dashboard |  | Trainee/Student Dashbord is a seprate dashboard that will only be show to Trainee and will contain things like Enroll Course , GradeBook, Calendar . | 3
4 | Profile |  | Profile Module contains basic informtaion of the user like Name,Username,Password,Email and Profile Pic etc. | 1
5 | Google Meet |  | Google Meet Module is an Api integration between Lms and Google meet that will allow Instructor and trainee to communicate using Google Meet through Lms | 4
| 5.1 | Api integeration |  | 4
| 5.2 | Google meet Integration with Course |  | 4
6 | Notifications |  | Notification Module shows notification to the trainee and instructor according to their role , accessibility and needs. | 3
7 | Calendar |  | Calender section contain calender view of quiz and assignmnets of all the courses for Trainee and Instructor | 3
8 | Multilingual |  | Lms App can be translate into other language like Arabic | 1
9 | Google Classroom |  | Google Classroom Module is an Api integration between Lms and Google Classroom that will allow Instructor and trainee to communicate using Google Classroom through Lms
| 9.1 | Api integeration |  | 4
| 9.2 | Google Classrom Integration with Course |  | 4
10 | Zoom |  | Zoom Module is an Api integration between Lms and Zoom that will allow Instructor and trainee to communicate using Zoom through Lms
|  | Api integeration |  | 4
|  | Zoom Integration with Course |  | 4
11 | Teams |  | Teams Module is an Api integration between Lms and Teams that will allow Instructor and trainee to communicate using Teams through Lms
| 11.1 | Api integeration |  | 4
| 11.2 | Zoome meet Integration with Course |  | 4
12 | Multi Instructor |  | Multi Instructor Module allows Multiple instructors to teach a single course to Trainess and communicate with them and provide quiz and assignments. | 2
13 | Reports |  | Reports Module allows Instructors and Trainees to see and download the csv file of their grades in courses for Traniee and Instructor can view and download the report of all the trainees grades | 3
14 | Assignments |  | Assignment Module allows the Instructor to give assignments to the Trainees and Trainees can see and submit the assignment | 2
15 | Quiz |  | Quiz Module allows the Instructor to give Quiz to the Trainees and Trainees can see and attempt the assignment | 3
Quiz builder (Multiple quiz types)
Quiz Attempts
Quiz Timer
16 | Q & A |  | Q&A Module allow Trainees to ask question regarding course to the course Instructor | 2
17 | Annoucements |  | Announcement Module allows Instructor to create an announcement regarding the course and this announcemnt will be notified to all the Trainees enrolled in that course | 2
18 | Prerequisites |  | Prerequisites Module will allow the Instructor to set a pre requiremnt course for new the course so the Trainee must complete the pre required course if he/she wants to enroll in the course | 2
19 | Gradebook |  | Gradebook Module will allow students to see their grades from all the course and will provide them their percentages or CGPA for the couse | 3
20 | Certificate |  | Certificate Module will allow Instructor to give certificate to the students that has completed the course which they can verify through QR code | 2
21 | Course Review |  | Course Review Module allows Trainees to provide their review of the course | 2
22 | E-Mail & SMS |  | Email & Sms Module will Send emails and msg to the Trainees regarding any new announcemnts or meetings with Instructor etc. | 3
23 | Analytics |  | Analytics Module provide a analytic View to the user regarding their activity on lms app | 2
24 | Course Attachments |  | Course Attachments module allow Instructor to add files to the course like pdf etc. | 2
25 | Course Creation |  | Course Creation allow the Instructor to Create a new Course and it has multiple settings that Instructor can use customize the course according to their requirements | 1
| 25.1 | Course Info |  | 1
| 25.2 | Course Settings |  | 1
| 25.3 | Course category |  | 1
| 25.4 | Course Thumbnail |  | 1
| 25.5 | Video |  | 1
| 25.6 | Course Builder |  | 1
| 25.7 | Zoom Meeting |  | 3
| 25.8 | Course Attachments |  | 2
| 25.9 | Additional Data |  | 4
| 25.1 | Course Prerequisites |  | 1
| 25.12 | Course Certificate |  | 4
26 | Bundel of courses |  | Bundle Course Module allow instructor to make a single course with multiple course in it like a bundle of courses | 2
My Courses
All Courses
Course Progress(Trainee)
RTL/LTR
Right to left and viceversa for Multilanguage
Multilingual
English, Arabic
27 | Home Page |  |  | 1
28 | About Us Page |  |  | 1
29 | Conatct Us Page |  |  | 1
30 | Courses Page |  |  | 2
31 | Bio Page |  |  | 1

## Sheet1
feature | Phase
Landing page and essential pages | 1
Tainee Registration and approval | 1
Course with basic features ( Offline - Online Content ) | 1
Course Bundle | 2
Traineer Registration | 2
Multi Assign for Trainers to specific course | 2
Adding Projects to courses | 2
Adding assignments to courses | 3
Add certification | 3
Add Quizez at the beginning and the end of course | 3
announcements | 4
integrate with ZOOM - MEET- TEAMS | 4
Calendar | 4
Reports for attendance and log activities | 4
General Admin panel | 4

## Secions Inputs & Tabs
Learning Management System (Sections, Inputs & Tabs)
S. # | Section | Input & Tabs
1 | Sign In | (Inputs: User name/Email and Password, Tabs: Forget Password and Singup Page, Button: LogIn)
2 | Sign Up | (inputs: Name, Father Name, National ID, Mobile Number, DOB, Working place, Latest Degree, Workign Company Name, Age Restriction, Email and Password, Tabs: Forget Password and SignInPage, Button: Register)
3 | Dashboard | Header Tabs: Instructor Info Section, Create New Course Button . DashBoard SideBar: Tabs(My Profile, Enrolled Courses, WishList, Reviews, My Quiz Attempt, Qusetion Answer, Calender, My Courses, Announcements, Withdrawals, Quiz Attempts, Assingments, Zoom, Certificate , Analytics Setting, LogOut) DashBoard Body (Numbers of Enrolled Courses, Active Courses, Completed Courses, Total Students, Total Courses, Total Earnings) My Courses Table :(Course Name , Enrolled, Rating)
student Info Section . DashBoard SideBar: Tabs(My Profile, Enrolled Courses, WishList, Reviews, My Quiz Attempt, Qusetion Answer, Calender, Setting, LogOut). DashBoard Bopdy (Numbers
4 | Profile | First Name, Last Name, Username, Email, Phone Number, National Id
5 | Google Meet Integration | Inputs (API Key, Secret Key), Button : Save/Checkconnection
6 | Notifications | CourseNotification, Announcemnt Notification, Assignment Notification,Quiz Notification
7 | Calender | Upcoming Assignments, Upcoming Quiz, Upcoming Sessions
8 | Zoom Integration | Inputs(API Key, Secret Key), Button : Save/Checkconnection
9 | Team Integration | Inputs(API Key, Secret Key), Button : Save/Checkconnection
10 | Multi Instructer | Select Instructor
11 | Assignment | Assignment Name, Total Marks,Total Submit , Details(Date,Student,Total Points,Result Detail(Course,Student,Submitted Date,Assignment Description,Evaluation(Your Points,Feedback, Button:Evaluate this submission)))
12 | My Quiz Attempts | Table(Quiz Info, Question, Total Marks, Correct Answer,Incorrect Answer,Earned Marks, Result, ) Button: Details, Details ( Course Name,Number, Quiz Time, Attempt Time, Table(Date,Question, Total Marks,Pass Marks,Correct Answer,Incorrect Answer,Earned Marks, Result)) Overview:(No, Type,Questions,Given Answer, Correct Answer,Result)
13 | Q&A | Student,Question,Course,Status , Button:Reply(Chat Section, Solved, Important, Archeived,Delete)
14 | Announcement | Date, Announcements,Details(Announcement Title,Summary,Course,Published Date , Edit ,Delete,Cancel), Add New Announcement(Select Course,Announcement Title,Summary)
15 | Prerequisites | Select Courses
16 | Certificate | Select Certificate Template For Course, Add QR code
17 | Course Review | Student,Date, Feedback(out of 5, Review Text, Course)
18 | Analytics | Overview(Total Course,Total Student,Reviews),Courses(Course(Lesson,AssignmentQuiz), Students), Students(Student,Registration Date,Course Taken, Detail(student Name,Course Date,Course,Progress Bar))
19 | Course Info | Course Title,Course Slug,,About Course
20 | Course Settings | Maximum Students,Difficulty Level,Q&A
21 | Course Catergory | Choose a category
22 | Course Thumnail | Attachment
23 | Video | Course Intro Video Upload
24 | Course Builder | Add Topics(Topic Name,Topic Summary)
25 | Course Attachments | Attach files
26 | Additional data | What Will I Learn,Total Course Duration,Materials Included,Requirements/Instructions
27 | Course Prerequisites | Select Course
28 | Course Certificate | Select Template
29 | Bundel of Courses | Course Name, Select Courses, Creation of Bundle
Additional Static Pages
1 | Home Page
2 | About Us Page
3 | Conatct Us Page
4 | Courses Page
5 | Bio Page